## AE-VMG Q2 Forecast
| Steps | Start Date | End Date | # of Days | Who
1 | Distribute Q2 Forecast calendar with link to training and refresh on how to update supporting WD workbooks | 2023-12-12 | 2023-12-12 | 1 | AE/VMG Finance
2 | BFT Personnel / Faculty Provider Change Forms open; Clincial provider position forms completed | 2023-12-12 | 2024-01-05 | 19 | Departments
3 | BFT Personnel / Faculty Provider Change Forms open; all other forms - Personnel & non-Clinical Faculty | 2023-12-12 | 2024-01-22 | 28 | Departments
4 | BFT Personnel Forms (Current Platform - Closes End of Day) | 2023-12-26 | 2023-12-26 | 1 | Departments
5 | BFT Personnel Forms (New Platform Transition) | 2023-12-27 | 2023-12-29 | 3 | Development Team
6 | BFT Personnel Forms (New Platform open & User functionality review session) | 2024-01-02 | 2024-01-02 | 1 | Finance/Departments
7 | Clinical Enterprise (excluding Clinical Departments) Fin Ops confer with Hospital Presidents, Division EVPs & VPs and relevant Chairs to obtain agreement on FY24 volumes forecasts Visits Target = Meet FY24 Budget OR Cases Target = Meet FY24 Budget | 2023-12-18 | 2024-01-05 | 15 | Clinical Operations & Finance
8 | New & departing provider volume projections (Visits & OR cases) communicated to Clinic Finance PCC Officers/VIP/VHS to coordinate volumes and Professional Revenue (wRVUs, Charges, & Collections) | 2024-01-05 | 2024-01-11 | 5 | Departments & Clinical Operations & Finance
9 | End User Training training sessions (9:30 Clinical Dept Session & 1:30 Non-Clinical Session) We will record and post on website. | 2024-01-08 | 2024-01-08 | 1 | Business Education
10 | December 2023 month-end close | 2024-01-05 | 2024-01-05 | 1 | All
11 | Final December General Ledger Close Meeting | 2024-01-10 | 2024-01-10 | 1 | Finance
12 | Run/confirm all Adaptive integrations/file uploads successful (with December General Ledger Actuals) & rollforward forecast version | 2024-01-11 | 2024-01-11 | 1 | Finance
13 | Updates for Intracompany elimination account activity (i.e., NashBio, VIS, etc.) will be communicated by AE/VMG Finance to respective areas for update in Adaptive | 2024-01-18 | 2024-01-18 | 1 | Finance & Departments
14 | Clinical Departments complete PB Revenue forecast in Adaptive (Finance Revenue team to consolidate across VUMC) | 2024-01-12 | 2024-01-22 | 5 | Departments
15 | Clinical and Non-Clinical Department CBOs/AOs finalize Personnel Forms in BFT. Confirm FY24 BFT changes are included in Adaptive Labor AE/MCA sheet. | 2024-01-12 | 2024-01-22 | 5 | Departments
16 | Clinical and Non-Clinical Department CBOs/AOs complete all modules in Adaptive for Q2 Forecast | 2024-01-12 | 2024-01-22 | 5 | Departments
17 | Clinical and Non-Clinical Department CBOs/AOs meet with Chairs or Center/Institute Directors to review and approve submissions | 2024-01-12 | 2024-01-22 | 5 | Departments
18 | Clinical and Non-Clinical Departments submit Adaptive Q2 Forecast and Financial Summary Variance explanation template to AE/VMG Finance with Clinical and Non-Clinical Department Chair or Center/Institute Director approval via email (send to budgetprofinance@vumc.org) | 2024-01-12 | 2024-01-22 | 1 | Departments
19 | AE/VMG Finance reviews Clinical and Non-Clinical Department, Center & Institute forecast submissions, completes AE/VMG Central Admin Department forecasts; Prepares Q2 Forecast presentations. | 2024-01-23 | 2024-01-29 | 5 | AE/VMG Finance
20 | FY25 Budget Kickoff | 2024-01-25 | 2024-02-01 | 6 | AE/VMG Finance
21 | AE/VMG Finance provides completed Forecast presentation to FP&A for VUMC consolidation | 2024-01-30 | 2024-01-30 | 1 | AE/VMG Finance
22 | Finalize Q2 Forecast for presentation | 2024-01-31 | 2024-01-31 | 1 | Finance
23 | FY24 Q2 Forecast BOD material review with Executive Leadership Team Meeting | 2024-02-05 | 2024-02-05 | 1 | Leadership
24 | Q2 Forecast complete (BOD Materials Posted) | 2024-02-09 | 2024-02-09 | 1 | Leadership

## AE-VMG FY25 Budget
| Scenario | Steps | Start Date | End Date | # of Days | Who
1 | Q2 Forecast | BFT Personnel Forms (Current Platform - Closes End of Day) | 2023-12-26 | 2023-12-26 | 1 | Departments
2 | Q2 Forecast | BFT Personnel Forms (New Platform Transition) | 2023-12-27 | 2023-12-29 | 3 | Development Team
3 | Q2 Forecast | BFT Personnel Forms (New Platform open & User functionality review session) | 2024-01-02 | 2024-01-02 | 1 | Finance/Departments
4 | FY25 Budget | AE/VMG Clinical Departments review and refresh FY25 Budget Clinical Provider forms in BFT (New/Replacement/Departing) to prepare for PB Revenue Adaptive load | 2024-01-02 | 2024-01-12 | 10 | Finance & Clinical Departments
5 | FY25 Budget | Finalize Non-Provider Personnel change forms to prepare for budget release | 2024-01-02 | 2024-01-26 | 24 | Departments
6 | FY25 Budget | Prepare Adaptive for FY25 Budget (Payroll data to be imported the week of January 15th) | 2024-01-11 | 2024-01-31 | 20 | Finance Systems, Fin Ops, FP&A
7 | Q2 Forecast | Clinical and Non-Clinical Departments submit Adaptive Q2 Forecast and Financial Summary Variance explanation template to AE/VMG Finance with Clinical and Non-Clinical Department Chair or Center/Institute Director approval via email (send to budgetprofinance@vumc.org) | 2024-01-12 | 2024-01-22 | 1 | Departments
8 | FY25 Budget | AE/VMG Clinical Departments FY25 Budget Clinical Providers (New/Replacement/Departing) consolidated for load to Adaptive | 2024-01-15 | 2024-01-19 | 4 | Finance
9 | FY25 Budget | FY25 Volume targets (at provider level detail) loaded into Adaptive including planned New providers | 2024-01-22 | 2024-01-26 | 4 | Finance Systems, Fin Ops, FP&A
10 | FY25 Budget | FY25 Budget presentation at Chair luncheon | 2024-01-25 | 2024-01-25 | 0 | Finance & Exec Leadership
11 | FY25 Budget | AE-VMG FY25 Budget Kickoff | 2024-01-29 | 2024-01-29 | 0 | Finance & Departments
12 |  | AE/VMG FY25 Budget Letter and Department Support schedules distributed | 2024-01-29 | 2024-02-01 | 3 | Finance & Departments
13 | FY25 Budget | AE-VMG FY25 Budget User Training - Adaptive | 2024-01-29 | 2024-02-06 | 8 | Business Education & Departments
14 | FY25 Budget | FY25 Budget volumes (visits, patient days, discharges, surgeries, key procedures) reviewed, edited, and finalized in Adaptive | 2024-02-01 | 2024-02-16 | 15 | PCC Managers & Departments
15 | FY25 Budget | Non-clinical Departments, Centers & Institutes complete budget in Adaptive | 2024-02-01 | 2024-02-29 | 28 | Departments
16 | FY25 Budget | Clinical Departments, Centers & Institutes complete budget in Adaptive | 2024-02-01 | 2024-03-07 | 35 | Departments
17 | FY25 Budget | FY25 Budget volumes in Adaptive compared to Plan Targets | 2024-02-19 | 2024-02-21 | 2 | Fin Ops, FP&A, AE/VMG Fin.
18 | FY25 Budget | Non-clinical Departments, Centers & Institutes submit budgets with Chair or Center/Institute Director approval | 2024-02-29 | 2024-02-29 | 0 | AE/VMG Budget Users; AE/VMG Chairs & Directors
19 | FY25 Budget | Clinical Departments submit budgets with Chair or Center/Institute Director approval | 2024-03-07 | 2024-03-07 | 0 | AE/VMG Budget Users; AE/VMG Chairs & Directors
20 | FY25 Budget | Finance reviews submissions & consolidates | 2024-03-08 | 2024-03-22 | 14 | Finance
21 | FY25 Budget | Executive Review, Finance Consolidate, Dept updates | 2024-03-22 | 2024-04-16 | 25 | Finance, Executive Leadership
22 | FY25 Budget | Clinical and Non-clinical Dept Budget Reviews - Chairs, CBO's, AO's | 2024-03-25 | 2024-04-05 | 11 | AE/VMG Fin & Departments
23 | FY25 Budget | FY25 Budget Spreads - begin to review spreads during final Executive reviews and adjust as needed. | 2024-03-26 | 2024-04-23 | 28 | Finance
24 | FY25 Budget | Complete BOD presentation materials | 2024-04-01 | 2024-05-12 | 41 | Finance
25 | FY25 Budget | Volumes sign-off obtained from Leadership | 2024-05-13 | 2024-05-31 | 18 | Fin Ops, Budget, Clinical Departments
26 | FY25 Budget | FY25 Budget presented at BOD Meeting | 2024-06-03 | 2024-06-04 | 1 | Finance